## Instructions
PRODUCT BACKLOG TEMPLATE
INSTRUCTIONS
Step 1: After writing the user stories and estimates, organize the stories into functions, features, deliverables, releases, etc.
Record the names of the headings for stories in the light blue bars. These are the main groups of product you need to deliver over time to provide customer value.
Step 2: Record the stories and estimates
Group them under their appropriate headings.
Step 3: Expand the number of rows as necessary.
Step 4: Collaborate with product owner.
Work with the product owner to fill in the priorities (in the example, MoSCoW is used). And the initial sprints planned for each story. When possible, finish everything under a heading in the same sprint
so more value can be delivered to the customer. Stories in the current sprint will also be copied to the Burndown Chart. Recording items that are not included will help to control the scope.
Step 5: Record the status at least weekly.
Color code the status (RAG = Red, Amber, Green, Blue for Completed). Actual points completed are recorded daily on the Burndown Chart.

## Product Backlog
ID | Story Title | Story Points | Priority | Planned Sprint | Status
Function / Feature #1
1
2
3
4
5
6
7
8
Function / Feature #2
9
10
11
12
13
14
15
16
Function / Feature #3 | Deliverable #1
17
18
19
20
21
22
23
24
Function / Feature #4 | Deliverable #2
19
20
21
22

## Product Backlog Pre-filled Ex
ID | Story Title | Story Points | Priority | Planned Sprint | Status
Administration Function
1 | Upload Movies | 5 | M | 1 | Completed
2 | Update Movie Prices | 2 | M | 1 | In Progress
3 | Correct Movie Data | 2 | M | 1 | In Progress
4 | Replace Movie Thumbnail |  | W |  | Wont' Have
5 | Add More Pricing Options |  | W |  | Wont' Have
6
7
8
Customer Purchase Function
9 | Search by Genre | 8 | M | 2 | Not Yet Started
10 | Search by Title | 2 | S | 3 | Not Yet Started
11 | Search by Reviews | 13 | C | 3 | Not Yet Started
12 | Search by Cast Members | 5 | S | 3 | Not Yet Started
13 | Tall Tale | 20 | M | 4 | Not Yet Started
14 | Epic Fail |  | W |  | Wont' Have
15
16
Customer Search Function
17 | Search by Genre | 8 | M | 1 | Completed
18 | Search by Title | 2 | S | 2 | In Progress
19 | Search by Reviews | 13 | C | 2 | Not Yet Started
20 | Search by Cast Members | 5 | S | 2 | In Progress
21
22
23
24
Function / Feature #4 | Deliverable #2
19
20
21
22